## Slide 2
Town Hall Meeting
Fellowship Hall and Gymnasium Addition
St. Mary Parish
Roman Catholic Diocese of Joliet
Plano, Illinois
March 23, 2017

## Slide 3
Souls
Space
School
Fr. Andy’s
Pastoral
Priorities

## Slide 4
Fellowship Hall / Meeting Space
Gymnasium
Administrative Offices
Additional Parking
Immediate
Needs

## Slide 5
St. Mary Parish
Fr. Andy Davy, MIC
Pastor
Anita Eversole
Business Manager
Joe Scarpino
School Principal
Rick Hanna
Parish Council Chair,
Finance Council Member
Omar & Rosa Espinosa
Capital Campaign
Chairpersons
Ken & Carole Nagel
Capital Campaign
Honorary Chairpersons

## Slide 6
Jacob Been, AIA,
LEED AP BD + C
Senior Architect
Clifford A. Bender, AIA
Principal In Charge
Director of Architecture
Architects
Planners

## Slide 7
2007
Master Plan

## Slide 8
Program

## Slide 10
Tier 1
Celebration Goal
8,500sf

## Slide 11
Tier 2
Challenge Goal
9,600sf

## Slide 12
Tier 3
Fr. Andy Victory Goal
15,400sf

## Slide 13
Concept Rendering
(Fr. Andy Victory Goal)

## Slide 14
Concept Rendering
(Fr. Andy Victory Goal)

## Slide 15
$
Preliminary
Project Budget

## Slide 17
Fundraising
Start date: Aug 2016
Estimated Fund Balance Aug 2019
$1,462,800
Chart: Tier 1 Cost: $2,000,000
| End of Period Balance | Funding Gap
 | 1462800 | 629200
Chart: Tier 2 Cost: $2,300,000
| End of Period Balance | Funding Gap
 | 1462800 | 837200
Chart: Tier 3 Cost: $3,700,000
| End of Period Balance | Funding Gap
 | 1462800 | 2237200
Fundraising August 2016 – August 2019 (assumes no additional fundraisers)

## Slide 18
Fundraising
Assumptions
Annual Project Cost Inflation: 2.5%
Annual Interest on Funds: 3.0%
Mortgage Interest Rate: 6.0%
Diocese requires 80% funds in bank
before construction can start

## Slide 19
Requires Additional Funding
Chart: Tier 1 Cost: $2,000,000
| End of Period Balance | Funding Gap
 | 1667600 | 424400
Chart: Tier 2 Cost: $2,300,000
| End of Period Balance | Funding Gap
 | 1667600 | 632400
Scenario 1
3 years fundraising
Annual car fundraiser
Construction Start: Spring 2020
Fundraising August 2016 – August 2019
$1,667,600
Fundraising

## Slide 20
Extend
fundraising
3 years
Fundraising
Chart: Tier 1 Cost: $2,253,000
 | 2092000
Chart: Tier 2 Cost: $2,585,000
 | 2092000
Scenario 2
3 years fundraising
Annual car fundraiser
Extend fundraising 3 years
Delay Construction Start: Spring 2023
Fundraising August 2016 – August 2022
$3,103,000
+$850,000
+$518,000

## Slide 21
Requires
$424 - 632K Mortgage
Chart: Tier 1 Cost: $2,000,000
| End of Period Balance | Funding Gap
 | 1667600 | 424400
Chart: Tier 2 Cost: $2,300,000
| End of Period Balance | Funding Gap
 | 1667600 | 632400
Scenario 3
3 years fundraising
Annual car fundraiser
Extend fundraising 3 years
Obtain mortgage for shortfall
Construction Start: Spring 2020
Fundraising August 2016 – August 2019
$1,667,600
Fundraising

## Slide 22
Timeline
Fundraising
3 Years
Design
6-8 Mos
Construction
14-16 Mos
Mar
2017
Fall
2019
Spring
2020
Fall
2021
Scenario 1/3
Fall
2022
Spring
2023
Summer
2024
Design
6-8 Mos
Construction
14-16 Mos
Fundraising
3 Years
Additional Fundraising
3 Years
Scenario 2

## Slide 23
Fundraising
3 Years
Design
6-8 Mos
Construction
14-16 Mos
Construction
14-16 Mos
Fundraising
3 Years
Additional Fundraising
3 Years
Timeline
Mar
2017
Fall
2019
Spring
2021
Fall
2022
Design
6-8 Mos
Late Fall/Winter
2023
Scenario 1/3
Scenario 2

## Slide 24
Q&A